## Incident Status
As of Apr 30
Month | Created | Resolved | Backlog
2018-01 | 4 | 0 | 4
2018-02 | 7 | 1
2018-03 | 2 | 8
2018-04 | 4 | 4
2018-05 | 7 | 1
2018-06 | 4 | 4
2018-07 | 13 | 9
2018-08 | 3 | 10
2018-09 | 3 | 5
2018-10 | 6 | 2
2018-11 | 2 | 3
2018-12 | 1 | 3
2019-01 | 7 | 1
2019-02 | 5 | 1
2019-03 | 3 | 5
2019-04 | 6 | 6
14 Backlog for Apr (as of Apr 30)
key | priority | summary | open duration | team
IMPM-1931 | P2 | Data API V2 - United States Money Market Funds TRI and United States Open-End Funds update ratio is Zero. | >60 Days | Data API V2
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | >60 Days | Data API V2
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | >60 Days | Data API V2
IMPM-2215 | P2 | Data API V2 - Portfolio Account holding imports degraded | >60 Days | Data API V2
IMPM-2277 | P2 | Research Feeds - USA Production Delayed. | >60 Days | Research Feeds
IMPM-2286 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | >60 Days | Data API V2
IMPM-2342 | P2 | Retail Sites (AU) - My Portfolio tab in morningstar.com.au is partially degraded | >60 Days | .com Operations
IMPM-2384 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | 41-60 Days | Quicktake
IMPM-2386 | P2 | Market Data Binary Feed Delivery - Lag in streaming options for quotes for DISNAT | 41-60 Days | Enterprise Component Markets
IMPM-2395 | P2 | Research Database - Intermittent RDB Outage in the weekend | 41-60 Days | DB Operations
IMPM-2416 | P2 | Retail Sites AU - MCA - Portfolio manager is down | 20-40 Days | .com Operations
IMPM-2418 | P2 | Office - UIS import service partially degraded | 20-40 Days | Office
IMPM-2420 | P2 | Office - Import process partially degraded for UK clients | 20-40 Days | Office
IMPM-2430 | P2 | Equity Non-Fundamental - Delay in Equity Rating USA file | <20 Days | Price Data

## Response Time
Company Goal: P1 Response Time < 30 mins, P2 Response Time < 1 hr
Month | P1 | P2
2018-01 | 0 | 0.28
2018-02 | 3.47 | 0.22
2018-03 | 0.42 | 0.17
2018-04 | 0 | 0.24
2018-05 | 0.23 | 0.27
2018-06 | 0.47 | 0.1
2018-07 | 0.2 | 0.47
2018-08 | 0 | 0.33
2018-09 | 0.08 | 0.17
2018-10 | 0 | 0.22
2018-11 | 0 | 1.02
2018-12 | 0 | 0.28
2019-01 | 0 | 0.2
2019-02 | 0 | 0.27
2019-03 | 0 | 0.07
2019-04 | 0 | 0.45

## Open Action Item
Duration | Incident Count
20-40 Days | 2
41-60 Days | 3
<20 Days | 3
>60 Days | 6
Duration | Team | AI Count
20-40 Days | Data Services | 1
20-40 Days | Quicktake | 2
20-40 Days | SAL | 1
41-60 Days | IT | 1
41-60 Days | Individual Investor Support | 2
41-60 Days | Real Time | 1
<20 Days | Data Products | 1
<20 Days | Data Services | 4
<20 Days | Database Operation | 1
>60 Days | Data Services | 9
>60 Days | Mumbai Support Development | 1

## Root Cause Analysis
Root Cause Breakdown Description
https://mswiki.morningstar.com/display/DATATO/Root+Cause+Breakdown
RCA Breakdown | Count
Application-Capacity | 12
Application-Defect | 11
Change-Scheduled | 8
Vendor | 8
Application-Bug | 7
Process | 6
Unknown | 6
Infrastructure-Configuration | 4
Infrastructure-Database | 4
Application-Performance | 3
Data-Completeness | 3
Human error | 3
Infrastructure-Capacity | 2
Infrastructure-Server | 2
Infrastructure-Storage | 2
Infrastructure-Network | 1

## Open Action Item List
key | priority | summary | created | rca key | action items ticket | action items created | action items resolved | Report Date | Open Duration | team | comments | Assignee | Reporter
IMPM-1931 | P2 | Data API V2 - United States Money Market Funds TRI and United States Open-End Funds update ratio is Zero. | 2018-09-28 05:08 | IMPM-1933 | DTC-9586 | 2018-10-12 14:58 |  | 2019-05-05 23:59 | 205.3757 | Data Services
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DSO-337 | 2018-10-22 11:30 |  | 2019-05-05 23:59 | 195.5201 | Data Services
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DSBA-85 | 2018-10-22 11:31 |  | 2019-05-05 23:59 | 195.5194 | Data Services
IMPM-2215 | P2 | Data API V2 - Portfolio Account holding imports degraded | 2019-01-16 22:33 | IMPM-2216 | DSO-451 | 2019-01-22 15:07 |  | 2019-05-05 23:59 | 103.3694 | Data Services
IMPM-2215 | P2 | Data API V2 - Portfolio Account holding imports degraded | 2019-01-16 22:33 | IMPM-2216 | DOPC-11684 | 2019-01-22 15:13 |  | 2019-05-05 23:59 | 103.3653 | Data Services
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | 2019-01-16 20:54 | IMPM-2214 | DTPA-4610 | 2019-01-23 11:35 |  | 2019-05-05 23:59 | 102.5167 | Data Services
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | 2019-01-16 20:54 | IMPM-2214 | DSO-454 | 2019-01-23 11:41 |  | 2019-05-05 23:59 | 102.5125 | Data Services
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | 2019-01-16 20:54 | IMPM-2214 | DSO-455 | 2019-01-23 11:53 |  | 2019-05-05 23:59 | 102.5042 | Data Services
IMPM-2277 | P2 | Research Feeds - USA Production Delayed. | 2019-02-19 18:09 | IMPM-2278 | DCMSD-7150 | 2019-02-22 04:31 |  | 2019-05-05 23:59 | 72.8111 | Mumbai Support Development
IMPM-2286 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | 2019-02-22 10:31 | IMPM-2287 | DTS-2379 | 2019-02-25 11:56 |  | 2019-05-05 23:59 | 69.5021 | Data Services
IMPM-2342 | P2 | Retail Sites (AU) - My Portfolio tab in morningstar.com.au is partially degraded | 2019-03-24 18:52 | IMPM-2343 | IISUP-5592 | 2019-03-26 03:15 |  | 2019-05-05 23:59 | 40.8639 | Individual Investor Support
IMPM-2358 | P2 | Office Cloud - Client Web Portal login degraded | 2019-04-01 13:17 | IMPM-2359 | DOPA-8086 | 2019-04-02 20:41 |  | 2019-05-05 23:59 | 33.1375 | Data Services
IMPM-2399 | P2 | Data API V2 - 1 Year Return" is duplicated incorrectly with the "YTD % | 2019-04-23 12:56 | IMPM-2401 | DOPC-12617 | 2019-04-15 14:22 |  | 2019-05-05 23:59 | 20.4007 | Data Services
IMPM-2384 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | 2019-04-15 11:25 | IMPM-2385 | QT-2801 | 2019-04-17 05:23 |  | 2019-05-05 23:59 | 18.775 | Quicktake
IMPM-2384 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | 2019-04-15 11:25 | IMPM-2385 | SAL-4116 | 2019-04-19 04:35 |  | 2019-05-05 23:59 | 16.8083 | SAL
IMPM-2384 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | 2019-04-15 11:25 | IMPM-2385 | QT-2806 | 2019-04-22 03:54 |  | 2019-05-05 23:59 | 13.8368 | Quicktake
IMPM-2386 | P2 | Market Data Binary Feed Delivery - Lag in streaming options for quotes for DISNAT | 2019-04-16 22:36 | IMPM-2387 | RT-22870 | 2019-04-18 00:09 |  | 2019-05-05 23:59 | 17.9931 | Real Time
IMPM-2395 | P2 | Research Database - Intermittent RDB Outage in the weekend | 2019-04-22 10:09 | IMPM-2396 | DBOPS-14820 | 2019-04-23 05:41 |  | 2019-05-05 23:59 | 12.7625 | Database Operation
IMPM-2395 | P2 | Research Database - Intermittent RDB Outage in the weekend | 2019-04-22 10:09 | IMPM-2396 | DSO-588 | 2019-04-24 18:24 |  | 2019-05-05 23:59 | 11.2326 | Data Services
IMPM-2399 | P2 | Data API V2 - 1 Year Return" is duplicated incorrectly with the "YTD % | 2019-04-23 12:56 | IMPM-2401 | DTPA-4974 | 2019-04-24 19:13 |  | 2019-05-05 23:59 | 11.1986 | Data Services
IMPM-2395 | P2 | Research Database - Intermittent RDB Outage in the weekend | 2019-04-22 10:09 | IMPM-2396 | DTC-12096 | 2019-04-29 15:59 |  | 2019-05-05 23:59 | 6.3333 | Data Services
IMPM-2406 | P2 | Equity API - Equity API Webservices Partially Degraded | 2019-04-30 12:08 | IMPM-2407 | MOCAL-6949 | 2019-05-02 01:00 |  | 2019-05-05 23:59 | 3.9576 | Data Products
IMPM-2416 | P2 | Retail Sites AU - MCA - Portfolio manager is down | 2019-05-09 20:07 | IMPM-2417 | IISUP-5709 | 2019-05-12 22:23 |  |  |  | Individual Investor Support
IMPM-2416 | P2 | Retail Sites AU - MCA - Portfolio manager is down | 2019-05-09 20:07 | IMPM-2417 | ISD-168140 | 2019-05-13 22:13 |  |  |  | IT

## Incident Backlog
key | rca key | priority | summary | status | tid and business service | reporter | assignee | client | actual start time | created | resolved | rca key created | rca key resolved | incident cause category | root cause breakdown | top 6 product | sz team | onset time | mitigation time | response time | response hours | resolve hours | rca | rca sla | sz involved | itops_did monitoring fire | sz_monitoring fire | comments
IMPM-1931 | IMPM-1933 | P2 | Data API V2 - United States Money Market Funds TRI and United States Open-End Funds update ratio is Zero. | Resolved | DATAAPI - Data API V2 | James Yao | Avinash Soni | Internal - Morningstar | 2018-09-28 04:33 | 2018-09-28 05:08 | 2018-09-28 08:46 | 2018-09-28 08:46 | 2018-10-15 16:29 | Application: Application Defect | Application-Capacity | Yes | Data API V2 | 2018-09-28 04:33 | 2018-09-28 08:46 | 2018-09-28 04:33 | 0 | 4.2167 | https://mswiki.morningstar.com/display/technology/DataAPI-V2_2018-09-28_IMPM-1931_Data+API+V2-+United+States+Money+Market+Funds+TRI+and+United+States+Open-End+Funds+update+ratio+is+Zero | RCA > 5 | Yes | No
IMPM-1972 | IMPM-1973 | P2 | DataAPI V2- DataAPI V2 service degraded. | Resolved | DATAAPI - Data API V2 | Vijaya Laxmi Reddy Narsa | Nazir Shaikh | Internal - Morningstar | 2018-10-11 09:54 | 2018-10-11 10:02 | 2018-10-11 12:05 | 2018-10-11 12:05 | 2018-10-12 13:15 | Capacity: Insufficient capacity in given service area | Application-Capacity | Yes | Data API V2 | 2018-10-11 09:49 | 2018-10-11 12:05 | 2018-10-11 09:55 | 0.1 | 2.2667 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=275723076 | RCA ≤ 5 | Yes | Yes
IMPM-2213 | IMPM-2214 | P2 | Data API V2 - Portfolio ownership API performance degraded | Resolved | DATAAPI - Data API V2 | James Yao | Sudarshan Dange | Internal - Morningstar | 2019-01-16 19:04 | 2019-01-16 20:54 | 2019-01-16 22:00 | 2019-01-16 22:00 | 2019-01-23 12:02 | Capacity: Insufficient capacity in given service area | Application-Capacity | Yes | Data API V2 | 2019-01-16 17:00 | 2019-01-16 22:00 | 2019-01-16 19:04 | 2.0667 | 5 | https://mswiki.morningstar.com/display/technology/DataAPI-V2_2019-01-16_IMPM-2213_Data+API+V2+-+Portfolio+ownership+API+performance+degraded | RCA ≤ 5 | Yes | No
IMPM-2215 | IMPM-2216 | P2 | Data API V2 - Portfolio Account holding imports degraded | Resolved | DATAAPI - Data API V2 | Rahul Shyam | Stevon Gomez | Internal - Morningstar | 2019-01-16 03:00 | 2019-01-16 22:33 | 2019-01-17 00:55 | 2019-01-17 00:55 | 2019-01-23 10:11 | Unknown: Root cause unknown | Application-Capacity | Yes | Data API V2 | 2019-01-16 21:35 | 2019-01-17 00:55 | 2019-01-16 21:37 | 0.033333 | 3.3333 | https://mswiki.morningstar.com/display/technology/DataAPI-V2_2019-01-16_IMPM-2215_Data+API+V2_Portfolio+Account+holding+imports+degraded | RCA ≤ 5 | Yes | No
IMPM-2277 | IMPM-2278 | P2 | Research Feeds - USA Production Delayed. | Closed | RP - Research Feeds | Surbhi Kumar | Akshay Soni | Internal - Morningstar | 2019-02-19 16:46 | 2019-02-19 18:09 | 2019-02-19 21:04 | 2019-02-19 21:04 | 2019-02-22 09:07 | Data: Problem due to data quality (collection or processing) | Data-Completeness | Yes | Research Feeds | 2019-02-19 17:30 | 2019-02-19 20:43 | 2019-02-19 17:56 | 0.43333 | 3.2167 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=287292673 | RCA ≤ 5 | Yes | No
IMPM-2286 | IMPM-2287 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | Closed | DATAAPI - Data API V2 | Vijaya Laxmi Reddy Narsa | Vishal Dikshit | Merrill Lynch | 2019-02-21 13:00 | 2019-02-22 10:31 | 2019-02-22 15:18 | 2019-02-22 15:18 | 2019-02-25 16:46 | Capacity: Insufficient capacity in given service area | Infrastructure-Server | Yes | Data API V2 | 2019-02-22 10:00 | 2019-02-22 15:18 | 2019-02-22 10:15 | 0.25 | 5.3 | https://mswiki.morningstar.com/display/technology/DataAPI-V2_2019-02-22_IMPM-2286_Data+API+V2+-+Merrill+Lynch+account+files+delayed | RCA ≤ 5 | Yes | No
IMPM-2342 | IMPM-2343 | P2 | Retail Sites (AU) - My Portfolio tab in morningstar.com.au is partially degraded | Resolved | AUT - Retail Sites (AU) | Kumar Rajpure | Nazir Shaikh | Internal - Morningstar | 2019-03-24 06:02 | 2019-03-24 18:52 | 2019-03-24 20:23 | 2019-03-24 20:23 | 2019-04-02 04:34 | Application: Application Defect | Process | No | .com Operations | 2019-03-24 18:28 | 2019-03-24 20:27 | 2019-03-24 18:35 | 0.11667 | 1.9833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=289788120 | RCA ≤ 5 | Yes | No
IMPM-2358 | IMPM-2359 | P2 | Office Cloud - Client Web Portal login degraded | Resolved | DIRECTPL - Office Cloud | Harshadeep Shinde | Harshadeep Shinde | Internal - Morningstar | 2019-04-01 12:24 | 2019-04-01 13:17 | 2019-04-01 13:33 | 2019-04-01 13:33 | 2019-04-12 03:30 | Application: Application Defect | Application-Defect | Yes | Direct/Office Cloud | 2019-04-01 10:24 | 2019-04-01 13:33 | 2019-04-01 10:30 | 0.1 | 3.15 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=291345688 | RCA ≤ 5 | Yes | Yes
IMPM-2384 | IMPM-2385 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | Resolved | AS - Quicktake | Lisamarie Nappier | Stevon Gomez | TD AMERITRADE | 2019-04-12 16:34 | 2019-04-15 11:25 | 2019-04-15 18:24 | 2019-04-15 18:24 | 2019-04-25 11:04 | Planned change: Scheduled change was the root cause | Change-Scheduled | Yes | Quicktake | 2019-04-15 11:10 | 2019-04-15 18:24 | 2019-04-15 11:34 | 0.4 | 7.2333 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=292569553 | RCA ≤ 5 | Yes | No
IMPM-2386 | IMPM-2387 | P2 | Market Data Binary Feed Delivery - Lag in streaming options for quotes for DISNAT | Resolved | RTD - Market Data Binary Feed Delivery | Billy Croxford | Sudarshan Dange | Internal - Morningstar | 2019-04-15 22:30 | 2019-04-16 22:36 | 2019-04-16 23:57 | 2019-04-16 23:57 | 2019-04-26 06:14 | Application: Application Defect | Application-Defect | Yes | Enterprise Component Markets | 2019-04-16 22:28 | 2019-04-16 22:30 | 2019-04-16 23:57 | 1.4833 | 0.033333 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=293112015 | RCA > 5 | Yes | No
IMPM-2395 | IMPM-2396 | P2 | Research Database - Intermittent RDB Outage in the weekend | Resolved | RDB - Research Database | Ashok Bachu | Rohan Singh | Internal - Morningstar | 2019-04-20 23:20 | 2019-04-22 10:09 | 2019-04-22 10:13 | 2019-04-22 10:13 | 2019-04-26 06:23 | Capacity: Insufficient capacity in given service area | Change-Scheduled | Yes | DB Operations | 2019-04-20 08:56 | 2019-04-21 03:19 | 2019-04-20 23:00 | 14.0667 | 18.3833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=293110756 | RCA ≤ 5 | Yes | Yes
IMPM-2399 | IMPM-2401 | P2 | Data API V2 - 1 Year Return" is duplicated incorrectly with the "YTD % | Closed | DATAAPI - Data API V2 | Amanda Duda | Akshay Soni | Internal - Morningstar | 2019-04-23 06:28 | 2019-04-23 12:56 | 2019-04-25 00:02 | 2019-04-25 00:02 | 2019-04-25 17:17 | Application: Application Defect | Application-Bug | Yes | Data API V2 | 2019-04-24 12:00 | 2019-04-21 03:19 | 2019-04-24 12:30 | 0.5 | -80.6833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=293121615 | RCA ≤ 5 | Yes | No
IMPM-2406 | IMPM-2407 | P2 | Equity API - Equity API Webservices Partially Degraded | Resolved | EQAPI - Equity API | Sweeto Thomas | Harshadeep Shinde | Internal - Morningstar | 2019-04-30 09:02 | 2019-04-30 12:08 | 2019-04-30 13:07 | 2019-04-30 13:07 | 2019-05-12 22:44 | Planned change: Scheduled change was the root cause | Change-Scheduled | Yes | Data Products | 2019-04-30 09:04 | 2019-04-30 13:05 | 2019-04-30 09:11 | 0.11667 | 4.0167 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=293134341 | RCA ≤ 5 | Yes | Yes
IMPM-2416 | IMPM-2417 | P2 | Retail Sites AU - MCA - Portfolio manager is down | Resolved | AUT - Retail Sites (AU) | Kumar Rajpure | Nazir Shaikh | Internal - Morningstar |  | 2019-05-09 20:07 | 2019-05-09 20:55 | 2019-05-09 20:55 | 2019-05-14 04:37 | Process design: Flaw in process design | Process | No | .com Operations | 2019-05-09 07:43 | 2019-05-09 08:54 | 2019-05-09 08:05 | 0.36667 | 1.1833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=294789663 | RCA ≤ 5 | Yes | Yes

## Incident list as of Apr 30
key | rca key | priority | summary | status | tid and business service | business service and technical component | reporter | assignee | client | actual start time | created | resolved | rca key created | rca key resolved | incident cause category | root cause breakdown | top 6 product | sz team | onset time | mitigation time | response time | response hours | resolve hours | rca | rca sla | sz involved | itops_did monitoring fire | sz_monitoring fire | comments
IMPM-2169 | IMPM-2170 | P2 | Equity API - Equity API Webservice is Partially Degraded | Closed | DATAOP - Ownership | Ownership - Ownership API | Aditya Katta | Jyoti Rao | Internal - Morningstar | 2019-01-03 10:33 | 2019-01-03 11:01 | 2019-01-03 13:00 | 2019-01-03 13:00 | 2019-01-06 19:28 | Planned change: Scheduled change was the root cause | Application-Capacity | Yes | Data Products | 2019-01-03 10:29 | 2019-01-03 13:01 | 2019-01-03 10:47 | 0.3 | 2.5333 | https://mswiki.morningstar.com/display/technology/Equity+API-IMPM-2170-20190103+Webservice+is+Partially+Degraded | RCA ≤ 5 | Yes | Yes
IMPM-2184 | IMPM-2185 | P2 | AWS - Hit with SQL Injection impacting ReleaseLive DB | Resolved | AWS - AWS | AWS - AWSE 2.0 | Ryan Lagasse | Tripura Kamble | Internal - Morningstar | 2019-01-09 15:30 | 2019-01-10 10:29 | 2019-01-10 10:34 | 2019-01-10 10:34 | 2019-01-23 12:43 | Application: Application Defect | Application-Defect | Yes | AWS | 2019-01-10 01:06 | 2019-01-10 09:05 | 2019-01-10 01:18 | 0.2 | 7.9833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=284007264 | RCA > 5 | Yes | No
IMPM-2195 | IMPM-2197 | P2 | Data Messaging - Kafka service partially degraded | Resolved | DP - Data Messaging | Data Messaging - Kafka-Connectors | Xiaoshuang Sun | Prashant Kumar | Internal - Morningstar | 2019-01-12 02:54 | 2019-01-14 03:27 | 2019-01-14 05:21 | 2019-01-14 03:27 | 2019-03-07 10:15 | Application: Application Defect | Vendor | Yes | Data Platform | 2019-01-14 03:10 | 2019-01-14 05:21 | 2019-01-14 03:12 | 0.033333 | 2.1833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=287294314 | RCA > 5 | Yes | No
IMPM-2213 | IMPM-2214 | P2 | Data API V2 - Portfolio ownership API performance degraded | Resolved | DATAAPI - Data API V2 | Data API V2 - Data API V2 | James Yao | Sudarshan Dange | Internal - Morningstar | 2019-01-16 19:04 | 2019-01-16 20:54 | 2019-01-16 22:00 | 2019-01-16 22:00 | 2019-01-23 12:02 | Capacity: Insufficient capacity in given service area | Application-Capacity | Yes | Data API V2 | 2019-01-16 17:00 | 2019-01-16 22:00 | 2019-01-16 19:04 | 2.0667 | 5 | https://mswiki.morningstar.com/display/technology/DataAPI-V2_2019-01-16_IMPM-2213_Data+API+V2+-+Portfolio+ownership+API+performance+degraded | RCA ≤ 5 | Yes | No
IMPM-2215 | IMPM-2216 | P2 | Data API V2 - Portfolio Account holding imports degraded | Resolved | DATAAPI - Data API V2 | Data API V2 - Data API V2 | Rahul Shyam | Stevon Gomez | Internal - Morningstar | 2019-01-16 03:00 | 2019-01-16 22:33 | 2019-01-17 00:55 | 2019-01-17 00:55 | 2019-01-23 10:11 | Unknown: Root cause unknown | Application-Capacity | Yes | Data API V2 | 2019-01-16 21:35 | 2019-01-17 00:55 | 2019-01-16 21:37 | 0.033333 | 3.3333 | https://mswiki.morningstar.com/display/technology/DataAPI-V2_2019-01-16_IMPM-2215_Data+API+V2_Portfolio+Account+holding+imports+degraded | RCA ≤ 5 | Yes | No
IMPM-2234 | IMPM-2235 | P2 | Fund Portfolio - Portfolio Partially Degraded | Resolved | DC - Fund Portfolio | Fund Portfolio - Fund Data Portfolio | Yang Gao | Asif Khan6 | Internal - Morningstar | 2019-01-29 23:14 | 2019-01-30 16:01 | 2019-01-30 16:52 | 2019-01-30 16:52 | 2019-03-27 06:10 | Planned change: Scheduled change was the root cause | Change-Scheduled | No | Data Collection | 2019-01-30 09:41 | 2019-01-30 16:46 | 2019-01-30 10:25 | 0.73333 | 7.0833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=286659707 | RCA > 5 | Yes | No
IMPM-2236 | IMPM-2237 | P2 | AWS - Service Partially degraded for clients Ameriprise and Wells Fargo | Closed | AWS - AWS | AWS - Global Hypo | Tripura Kamble | Tripura Kamble | Ameriprise Financial | 2019-01-31 | 2019-01-31 03:49 | 2019-01-31 11:15 | 2019-01-31 11:15 | 2019-02-06 12:57 | Planned change: Scheduled change was the root cause | Change-Scheduled | Yes | AWS | 2019-01-31 00:25 | 2019-01-31 11:00 | 2019-01-31 00:28 | 0.05 | 10.5833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=284998371 | RCA ≤ 5 | Yes | No
IMPM-2266 | IMPM-2267 | P2 | Equity Data Feeds - Multiple clients reported earning reports data missing in delta file since 1/31 | Resolved | GED - Equity Data Feeds | Equity Data Feeds - GEDF | Berry Yu | Pratik Vegad | Internal - Morningstar | 2019-01-31 23:59 | 2019-02-12 11:56 | 2019-02-12 11:57 | 2019-02-12 11:57 | 2019-03-15 03:05 | Planned change: Scheduled change was the root cause | Application-Bug | No | Data Products | 2019-02-08 16:23 | 2019-02-11 13:38 | 2019-02-08 16:30 | 0.11667 | 69.25 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=286663266 | RCA ≤ 5 | Yes | No |  | Incident created after issue resolved
IMPM-2272 | IMPM-2273 | P2 | Office Cloud - Client Web Portal is completely Degraded | Resolved | DIRECTPL - Office Cloud | Office Cloud - DataService API | Bryanna Adams | Jyoti Rao | Internal - Morningstar | 2019-02-15 09:35 | 2019-02-15 09:49 | 2019-02-15 10:00 | 2019-02-15 10:00 | 2019-03-13 13:41 | Application: Application Defect | Unknown | Yes | Direct/Office Cloud | 2019-02-15 08:47 | 2019-02-15 10:02 | 2019-02-15 09:02 | 0.25 | 1.25 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=287301065 | RCA > 5 | Yes | Yes
IMPM-2277 | IMPM-2278 | P2 | Research Feeds - USA Production Delayed. | Closed | RP - Research Feeds | Research Feeds - Research Feeds | Surbhi Kumar | Akshay Soni | Internal - Morningstar | 2019-02-19 16:46 | 2019-02-19 18:09 | 2019-02-19 21:04 | 2019-02-19 21:04 | 2019-02-22 09:07 | Data: Problem due to data quality (collection or processing) | Data-Completeness | Yes | Research Feeds | 2019-02-19 17:30 | 2019-02-19 20:43 | 2019-02-19 17:56 | 0.43333 | 3.2167 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=287292673 | RCA ≤ 5 | Yes | No
IMPM-2286 | IMPM-2287 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | Closed | DATAAPI - Data API V2 | Data API V2 - Data API V2 | Vijaya Laxmi Reddy Narsa | Vishal Dikshit | Merrill Lynch | 2019-02-21 13:00 | 2019-02-22 10:31 | 2019-02-22 15:18 | 2019-02-22 15:18 | 2019-02-25 16:46 | Capacity: Insufficient capacity in given service area | Infrastructure-Server | Yes | Data API V2 | 2019-02-22 10:00 | 2019-02-22 15:18 | 2019-02-22 10:15 | 0.25 | 5.3 | https://mswiki.morningstar.com/display/technology/DataAPI-V2_2019-02-22_IMPM-2286_Data+API+V2+-+Merrill+Lynch+account+files+delayed | RCA ≤ 5 | Yes | No
IMPM-2295 | IMPM-2298 | P2 | Import Service - Merrill Lynch account files not successfully processed | Resolved | IMP - Import Service DWM | Import Service (DWM) - Central Import System | Eileen Bingle | Prashant Kumar | Merrill Lynch | 2019-02-26 03:17 | 2019-02-26 15:43 | 2019-02-26 18:25 | 2019-02-26 18:25 | 2019-02-28 23:17 | Capacity: Insufficient capacity in given service area | Data-Completeness | Yes | Import Service | 2019-02-26 15:00 | 2019-02-26 18:25 | 2019-02-26 15:17 | 0.28333 | 3.4167 | https://mswiki.morningstar.com/display/technology/IMP_Cloud_20190226_IMPM-2295_Import+Service+-+Merrill+Lynch+account+files+not+successfully+processed | RCA ≤ 5 | Yes | No
IMPM-2322 | IMPM-2323 | P2 | Direct Cloud - Office cloud's service partially degraded by a scheduled patch release | Resolved | DIRECTPL - Direct Cloud | Direct Cloud - Direct Cloud Shared Services | Kevin Ke | Prashant Kumar | Internal - Morningstar | 2019-03-06 19:05 | 2019-03-06 22:39 | 2019-03-07 03:48 | 2019-03-07 03:48 | 2019-03-27 06:12 | Planned change: Scheduled change was the root cause | Change-Scheduled | Yes | Direct/Office Cloud | 2019-03-06 22:05 | 2019-03-07 03:48 | 2019-03-06 22:09 | 0.066667 | 5.7167 | https://msjira.morningstar.com/browse/IMPM-2323 | RCA > 5 | Yes | No
IMPM-2330 | IMPM-2331 | P2 | Data API V2 - Data API V2 Performance Degraded | Resolved | DATAAPI - Data API V2 | Data API V2 - Data API V2 | Minerva Li | Harshadeep Shinde | Internal - Morningstar | 2019-03-15 01:34 | 2019-03-15 04:42 | 2019-03-15 05:25 | 2019-03-15 05:25 | 2019-03-25 03:26 | Application: Application Defect | Process | Yes | Data API V2 | 2019-03-15 01:34 | 2019-03-15 04:02 | 2019-03-15 01:39 | 0.083333 | 2.4667 | https://mswiki.morningstar.com/pages/viewpage.action?spaceKey=technology&title=DataAPI-V2_2018-10-11_IMPM-2230_DataAPI+V2-+Data+API+V2+Performance+Degraded | RCA ≤ 5 | Yes | Yes
IMPM-2342 | IMPM-2343 | P2 | Retail Sites (AU) - My Portfolio tab in morningstar.com.au is partially degraded | Resolved | AUT - Retail Sites (AU) | Retail Sites (AU) - Portfolio Manager | Kumar Rajpure | Nazir Shaikh | Internal - Morningstar | 2019-03-24 06:02 | 2019-03-24 18:52 | 2019-03-24 20:23 | 2019-03-24 20:23 | 2019-04-02 04:34 | Application: Application Defect | Process | No | .com Operations | 2019-03-24 18:28 | 2019-03-24 20:27 | 2019-03-24 18:35 | 0.11667 | 1.9833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=289788120 | RCA ≤ 5 | Yes | No
IMPM-2344 | IMPM-2345 | P2 | Retail Sites (AU) - My Portfolio tab in morningstar.com.au is partially degraded | Resolved | AUT - Retail Sites (AU) | Retail Sites (AU) - Portfolio Manager | Kumar Rajpure | Nazir Shaikh | Internal - Morningstar | 2019-03-24 23:20 | 2019-03-25 00:23 | 2019-03-25 01:28 | 2019-03-25 01:28 | 2019-04-02 04:33 | Application: Application Defect | Infrastructure-Server | No | .com Operations | 2019-03-25 00:15 | 2019-03-25 01:28 | 2019-03-25 00:23 | 0.13333 | 1.2167 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=289788120 | RCA ≤ 5 | Yes | No
IMPM-2358 | IMPM-2359 | P2 | Office Cloud - Client Web Portal login degraded | Resolved | DIRECTPL - Office Cloud | Office Cloud - DataService API | Harshadeep Shinde | Harshadeep Shinde | Internal - Morningstar | 2019-04-01 12:24 | 2019-04-01 13:17 | 2019-04-01 13:33 | 2019-04-01 13:33 | 2019-04-12 03:30 | Application: Application Defect | Application-Defect | Yes | Direct/Office Cloud | 2019-04-01 10:24 | 2019-04-01 13:33 | 2019-04-01 10:30 | 0.1 | 3.15 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=291345688 | RCA ≤ 5 | Yes | Yes
IMPM-2384 | IMPM-2385 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | Resolved | AS - Quicktake | Quicktake - Security Research Team | Lisamarie Nappier | Stevon Gomez | TD AMERITRADE | 2019-04-12 16:34 | 2019-04-15 11:25 | 2019-04-15 18:24 | 2019-04-15 18:24 | 2019-04-25 11:04 | Planned change: Scheduled change was the root cause | Change-Scheduled | Yes | Quicktake | 2019-04-15 11:10 | 2019-04-15 18:24 | 2019-04-15 11:34 | 0.4 | 7.2333 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=292569553 | RCA ≤ 5 | Yes | No
IMPM-2386 | IMPM-2387 | P2 | Market Data Binary Feed Delivery - Lag in streaming options for quotes for DISNAT | Resolved | RTD - Market Data Binary Feed Delivery | Market Data Binary Feed Delivery - IP Feed | Billy Croxford | Sudarshan Dange | Internal - Morningstar | 2019-04-15 22:30 | 2019-04-16 22:36 | 2019-04-16 23:57 | 2019-04-16 23:57 | 2019-04-26 06:14 | Application: Application Defect | Application-Defect | Yes | Enterprise Component Markets | 2019-04-16 22:28 | 2019-04-16 22:30 | 2019-04-16 23:57 | 1.4833 | 0.033333 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=293112015 | RCA > 5 | Yes | No
IMPM-2395 | IMPM-2396 | P2 | Research Database - Intermittent RDB Outage in the weekend | Resolved | RDB - Research Database | Research Database - EquityProduction | Ashok Bachu | Rohan Singh | Internal - Morningstar | 2019-04-20 23:20 | 2019-04-22 10:09 | 2019-04-22 10:13 | 2019-04-22 10:13 | 2019-04-26 06:23 | Capacity: Insufficient capacity in given service area | Change-Scheduled | Yes | DB Operations | 2019-04-20 08:56 | 2019-04-21 03:19 | 2019-04-20 23:00 | 14.0667 | 18.3833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=293110756 | RCA ≤ 5 | Yes | Yes
IMPM-2399 | IMPM-2401 | P2 | Data API V2 - 1 Year Return" is duplicated incorrectly with the "YTD % | Closed | DATAAPI - Data API V2 | Data API V2 - Data API V2 | Amanda Duda | Akshay Soni | Internal - Morningstar | 2019-04-23 06:28 | 2019-04-23 12:56 | 2019-04-25 00:02 | 2019-04-25 00:02 | 2019-04-25 17:17 | Application: Application Defect | Application-Bug | Yes | Data API V2 | 2019-04-24 12:00 | 2019-04-21 03:19 | 2019-04-24 12:30 | 0.5 | -80.6833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=293121615 | RCA ≤ 5 | Yes | No
IMPM-2406 | IMPM-2407 | P2 | Equity API - Equity API Webservices Partially Degraded | Resolved | EQAPI - Equity API | Equity API - Equity API Webservice | Sweeto Thomas | Harshadeep Shinde | Internal - Morningstar | 2019-04-30 09:02 | 2019-04-30 12:08 | 2019-04-30 13:07 | 2019-04-30 13:07 | 2019-05-12 22:44 | Planned change: Scheduled change was the root cause | Change-Scheduled | Yes | Data Products | 2019-04-30 09:04 | 2019-04-30 13:05 | 2019-04-30 09:11 | 0.11667 | 4.0167 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=293134341 | RCA ≤ 5 | Yes | Yes
IMPM-2416 | IMPM-2417 | P2 | Retail Sites AU - MCA - Portfolio manager is down | Resolved | AUT - Retail Sites (AU) | Retail Sites (AU) - Morningstar.com.au Website | Kumar Rajpure | Nazir Shaikh | Internal - Morningstar |  | 2019-05-09 20:07 | 2019-05-09 20:55 | 2019-05-09 20:55 | 2019-05-14 04:37 | Process design: Flaw in process design | Process | No | .com Operations | 2019-05-09 07:43 | 2019-05-09 08:54 | 2019-05-09 08:05 | 0.36667 | 1.1833 | https://mswiki.morningstar.com/pages/viewpage.action?pageId=294789663 | RCA ≤ 5 | Yes | Yes
IMPM-2418 | IMPM-2419 | P2 | Office - UIS import service partially degraded | Resolved | DO - Office | Office - Office BOS | Will Riley | Prashant Kumar | Internal - Morningstar | 2019-05-12 20:27 | 2019-05-13 05:48 | 2019-05-13 06:37 | 2019-05-13 06:37 |  | Planned change: Scheduled change was the root cause |  | No | Office | 2019-05-13 05:33 | 2019-05-13 06:38 | 2019-05-13 05:37 | 0.066667 | 1.0833 |  |  | Yes | No
IMPM-2420 | IMPM-2421 | P2 | Office - Import process partially degraded for UK clients | Resolved | DO - Office | Office - ClientSite-UK | Mike Degiovanni | Prashant Kumar | Internal - Morningstar | 2019-05-12 20:27 | 2019-05-13 11:24 | 2019-05-13 11:44 | 2019-05-13 11:44 |  | Planned change: Scheduled change was the root cause |  | No | Office | 2019-05-13 11:00 | 2019-05-13 11:46 | 2019-05-13 11:07 | 0.11667 | 0.76667 |  |  | Yes | No
IMPM-2430 | IMPM-2431 | P2 | Research Feeds - Delay in Equity Rating USA file | Resolved | RP - Research Feeds | Research Feeds - Research Feeds | Surbhi Kumar | Nazir Shaikh | Internal - Morningstar | 2019-05-17 16:19 | 2019-05-17 17:56 | 2019-05-17 21:24 | 2019-05-17 21:24 |  | Data: Problem due to data quality (collection or processing) |  | No | Price Data | 2019-05-17 16:19 | 2019-05-17 20:54 | 2019-05-17 16:20 | 0.016667 | 4.5833 |  |  | Yes | No