## Action Items List
key | priority | summary | created | rca key | action items ticket | action items created | action items resolved | Duration | Report Date | Open Duration | team | comments | Assignee | Reporter
IMPM-1288 | P2 | Portfolio Manager - Degraded Performance for Portfolio Manager | 2018-01-01 12:50 | IMPM-1289 | IISUP-4276 | 2018-01-01 12:50 | 2018-01-10 02:27 | 8.5674 | 2019-01-16 |  | Individual Investor Support | Use the Incident created date as Action Items Created
IMPM-1288 | P2 | Portfolio Manager - Degraded Performance for Portfolio Manager | 2018-01-01 12:50 | IMPM-1289 | IISUP-4283 | 2018-01-03 08:39 | 2018-03-08 19:45 | 64.4625 |  |  | Individual Investor Support
IMPM-1288 | P2 | Portfolio Manager - Degraded Performance for Portfolio Manager | 2018-01-01 12:50 | IMPM-1289 | IISUP-4287 | 2018-01-03 10:43 | 2018-04-30 11:13 | 117.0208 |  |  | Individual Investor Support
IMPM-1301 | P2 | Enterprise Components - Markets - Degraded performance for Markets | 2018-01-09 08:21 | IMPM-1302 | NEWS-785 | 2018-01-10 23:50 | 2018-01-15 05:12 | 4.2236 |  |  | News
IMPM-1301 | P2 | Enterprise Components - Markets - Degraded performance for Markets | 2018-01-09 08:21 | IMPM-1302 | NEWS-788 | 2018-01-18 04:21 | 2018-01-22 02:33 | 3.925 |  |  | News
IMPM-1301 | P2 | Enterprise Components - Markets - Degraded performance for Markets | 2018-01-09 08:21 | IMPM-1302 | QS-12257 | 2018-01-09 21:41 | 2018-01-18 03:32 | 8.2438 |  |  | Enterprise Component Markets
IMPM-1301 | P2 | Enterprise Components - Markets - Degraded performance for Markets | 2018-01-09 08:21 | IMPM-1302 | INSTSRE-187 | 2018-01-23 08:05 | 2018-02-01 13:28 | 9.2243 |  |  | Institutional Products SRE
IMPM-1301 | P2 | Enterprise Components - Markets - Degraded performance for Markets | 2018-01-09 08:21 | IMPM-1302 | INSTSRE-188 | 2018-01-23 08:08 | 2018-02-01 13:30 | 9.2236 |  |  | Institutional Products SRE
IMPM-1301 | P2 | Enterprise Components - Markets - Degraded performance for Markets | 2018-01-09 08:21 | IMPM-1302 | NEWS-793 | 2018-01-23 21:11 | 2018-03-23 00:38 | 58.1437 |  |  | News
IMPM-1301 | P2 | Enterprise Components - Markets - Degraded performance for Markets | 2018-01-09 08:21 | IMPM-1302 | NEWS-796 | 2018-01-24 03:31 | 2018-03-23 00:34 | 57.8771 |  |  | News
IMPM-1317 | P2 | Enterprise Components Markets - Degraded performance for Markets | 2018-01-15 10:08 | IMPM-1318 | QS-12330 | 2018-01-23 20:40 | 2018-03-27 20:18 | 62.9847 |  |  | Enterprise Component Markets
IMPM-1325 | P2 | Enterprise Components Markets - Research Screener issue. | 2018-01-21 20:49 | IMPM-1326 | DOV-1533 | 2018-01-24 03:49 | 2018-03-13 03:49 | 48 |  |  | Direct/Office
IMPM-1325 | P2 | Enterprise Components Markets - Research Screener issue. | 2018-01-21 20:49 | IMPM-1326 | DOV-1534 | 2018-01-24 03:53 | 2018-01-28 20:52 | 4.7076 |  |  | Direct/Office
IMPM-1356 | P2 | Enterprise Components Markets - Markets services severely degraded | 2018-02-06 10:17 | IMPM-1357 | RT-12039 | 2018-02-06 10:17 | 2018-03-01 08:10 | 22.9118 |  |  | Real Time | Use the Incident created date as Action Items Created
IMPM-1369 | P2 | Data API V2 - Database Server Outage | 2018-02-13 00:09 | IMPM-1371 | DSO-179 | 2018-02-15 16:40 | 2018-04-09 16:24 | 52.9889 |  |  | Data Services
IMPM-1369 | P2 | Data API V2 - Database Server Outage | 2018-02-13 00:09 | IMPM-1371 | DTPA-3497 | 2018-02-13 00:09 | 2018-02-14 17:20 | 1.716 |  |  | Data Services | Use the Incident created date as Action Items Created
IMPM-1373 | P1 | Enterprise Component Markets - EC Market service degraded. | 2018-02-14 13:26 | IMPM-1374 | ISD-87465 | 2018-02-14 13:26 | 2018-03-28 00:50 | 41.475 |  |  | IT | Use the Incident created date as Action Items Created
IMPM-1377 | P2 | Enterprise Component Markets - Multiple Critical Alerts fired on Truesight | 2018-02-15 02:04 | IMPM-1378 | IOT-1380 | 2018-02-15 04:05 | 2018-02-22 10:29 | 7.2667 |  |  | IT
IMPM-1381 | P2 | Enterprise Component Markets - Multiple Critical Alerts fired on Truesight | 2018-02-19 02:22 | IMPM-1382 | QS-12478 | 2018-03-07 19:57 | 2018-03-08 12:02 | 0.67014 |  |  | Enterprise Component Markets
IMPM-1383 | P2 | Fund XOI Frontend - HTTP errors while connecting to XOI | 2018-02-19 05:46 | IMPM-1384 | IOT-1804 | 2018-05-16 08:45 | 2018-05-29 14:32 | 13.241 |  |  | IT
IMPM-1383 | P2 | Fund XOI Frontend - HTTP errors while connecting to XOI | 2018-02-19 05:46 | IMPM-1384 | DPO-10388 | 2018-05-10 10:37 | 2018-05-16 08:49 | 5.925 |  |  | Data Operations
IMPM-1394 | P2 | Fixed Income - High response times from the bond service | 2018-02-28 14:48 | IMPM-1395 | DBOPS-10181 | 2018-03-01 00:52 | 2018-03-19 20:46 | 18.8292 |  |  | Database Operation
IMPM-1394 | P2 | Fixed Income - High response times from the bond service | 2018-02-28 14:48 | IMPM-1395 | DBOPS-10186 | 2018-03-01 13:06 | 2018-03-09 09:27 | 7.8479 |  |  | Database Operation
IMPM-1415 | P2 | Enterprise Component Markets - DISNAT SLA critical alerts generated in Truesight | 2018-03-19 07:47 | IMPM-1416 | QS-12517 | 2018-03-19 23:24 | 2018-03-22 05:13 | 2.2424 |  |  | Enterprise Component Markets
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DOPA-5564 | 2018-03-21 02:33 | 2018-03-27 02:15 | 5.9875 |  |  | Data Services
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DOPA-5566 | 2018-03-21 02:44 | 2018-03-21 22:48 | 0.83611 |  |  | Data Services
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DCF-6016 | 2018-03-21 01:36 | 2018-03-21 05:14 | 0.15139 |  |  | Direct Cloud
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DTPA-3713 | 2018-03-28 11:15 | 2018-04-02 16:24 | 5.2146 |  |  | Data Services
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DSO-200 | 2018-03-21 11:51 | 2018-04-02 09:50 | 11.916 |  |  | Data Services
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DTPA-3705 | 2018-03-22 16:47 | 2018-04-12 15:19 | 20.9389 |  |  | Data Services
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DOPC-7904 | 2018-03-14 11:03 | 2018-03-28 09:44 | 13.9451 |  |  | Data Services
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DTPA-3678 | 2018-03-19 11:56 | 2018-04-10 14:53 | 22.1229 |  |  | Data Services
IMPM-1424 | P1 | Data API V2 - DATA API V2 severely degraded | 2018-03-21 02:54 | IMPM-1425 | DTPA-3707 | 2018-03-27 11:16 | 2018-04-02 16:44 | 6.2278 |  |  | Data Services
IMPM-1447 | P2 | Data API V2 - DATA API V2 severely degraded | 2018-04-05 13:24 | IMPM-1425 | DOPA-5564 | 2018-03-21 02:33 | 2018-03-27 02:15 | 5.9875 |  |  | Data Services | The same root cause and action items with IMPM-1425
IMPM-1449 | P2 | Data API V2 - DATA API V2 severely degraded | 2018-04-05 13:33 | IMPM-1425 | DOPA-5564 | 2018-03-21 02:33 | 2018-03-27 02:15 | 5.9875 |  |  | Data Services | The same root cause and action items with IMPM-1425
IMPM-1454 | P2 | Real time Data- Realtime Webservice is degraded | 2018-04-09 10:26 | IMPM-1455 | RT-16151 | 2018-04-26 12:02 | 2018-04-26 12:03 | 0.00069444 |  |  | Real Time
IMPM-1476 | P2 | Artifact Repository - Nexus severely degraded | 2018-04-26 22:14 | IMPM-1478 | ENGRTASK-15045 | 2018-04-12 16:43 | 2018-06-26 02:41 | 74.4153 |  |  | Engineering | ETA for Nexus Prod upgrade is end of June
IMPM-1483 | P2 | Fund Performance - Direct Currency Conversion functionality is degraded | 2018-04-30 07:31 | IMPM-1484 | DPO-10359 | 2018-05-09 03:38 | 2018-06-19 04:38 | 41.0417 |  |  | Data Operations
IMPM-1483 | P2 | Fund Performance - Direct Currency Conversion functionality is degraded | 2018-04-30 07:31 | IMPM-1484 | MRDPM-15475 | 2018-05-09 05:11 | 2018-05-10 04:11 | 0.95833 |  |  | Data Collection
IMPM-1483 | P2 | Fund Performance - Direct Currency Conversion functionality is degraded | 2018-04-30 07:31 | IMPM-1484 | DBOPS-11483 | 2018-05-09 05:07 | 2018-06-14 03:47 | 35.9444 |  |  | Database Operation
IMPM-1530 | P2 | DataApiV1 - FundApi is experiencing timeout issue from DataApiV1 for investmentID | 2018-05-22 08:06 | IMPM-1531 | APPOPS-148 | 2018-06-06 00:53 | 2018-07-12 15:53 | 36.625 |  |  | IT
IMPM-1540 | P2 | Big Data Management - Kafka service failure which degraded DATAAPIV2 performance | 2018-05-24 07:51 | IMPM-1541 | CORESVC-4256 | 2018-06-06 04:31 | 2018-06-27 10:04 | 21.2312 |  |  | Core Service
IMPM-1540 | P2 | Big Data Management - Kafka service failure which degraded DATAAPIV2 performance | 2018-05-24 07:51 | IMPM-1541 | CORESVC-4258 | 2018-06-06 04:39 | 2018-07-10 02:47 | 33.9222 |  |  | Core Service
IMPM-1540 | P2 | Big Data Management - Kafka service failure which degraded DATAAPIV2 performance | 2018-05-24 07:51 | IMPM-1541 | CORESVC-4259 | 2018-06-06 04:41 | 2018-06-13 05:57 | 7.0528 |  |  | Core Service
IMPM-1540 | P2 | Big Data Management - Kafka service failure which degraded DATAAPIV2 performance | 2018-05-24 07:51 | IMPM-1541 | CORESVC-4257 | 2018-06-06 04:35 | 2018-06-06 04:36 | 0.00069444 |  |  | Core Service
IMPM-1540 | P2 | Big Data Management - Kafka service failure which degraded DATAAPIV2 performance | 2018-05-24 07:51 | IMPM-1541 | CORESVC-4260 | 2018-06-06 04:46 | 2018-06-07 00:54 | 0.83889 |  |  | Core Service
IMPM-1544 | P2 | Real Time Data - Performance degraded for Direct and Office | 2018-05-25 01:41 | IMPM-1546 | DOV-1823 | 2018-05-30 05:32 | 2018-07-06 01:45 | 36.8424 |  |  | Direct/Office
IMPM-1544 | P2 | Real Time Data - Performance degraded for Direct and Office | 2018-05-25 01:41 | IMPM-1546 | DOV-1824 | 2018-05-30 05:37 | 2018-07-06 02:02 | 36.8507 |  |  | Direct/Office
IMPM-1544 | P2 | Real Time Data - Performance degraded for Direct and Office | 2018-05-25 01:41 | IMPM-1546 | DOV-1826 | 2018-05-31 02:13 | 2019-04-08 09:27 | 312.3014 | 2019-04-08 23:59 | 312.9069 | Direct/Office | Feedback from Maksim Rudenko: Due to higher priority releases and blackouts, the prod deployment of the final action item on the ticket has been moved to the March 5th release.
IMPM-1544 | P2 | Real Time Data - Performance degraded for Direct and Office | 2018-05-25 01:41 | IMPM-1546 | MOCAL-5394 | 2018-05-27 21:40 | 2018-05-30 03:48 | 2.2556 |  |  | Data Products
IMPM-1544 | P2 | Real Time Data - Performance degraded for Direct and Office | 2018-05-25 01:41 | IMPM-1546 | RT-14511 | 2018-05-09 11:21 | 2018-05-29 15:30 | 20.1729 |  |  | Real Time
IMPM-1547 | P2 | Direct - Performance degraded for Direct and Office | 2018-05-25 09:40 | IMPM-1548 | DOV-1828 | 2018-05-31 04:44 | 2018-06-10 04:25 | 9.9868 |  |  | Direct/Office
IMPM-1547 | P2 | Direct - Performance degraded for Direct and Office | 2018-05-25 09:40 | IMPM-1548 | DOV-1829 | 2018-05-31 04:47 | 2018-06-10 04:26 | 9.9854 |  |  | Direct/Office
IMPM-1547 | P2 | Direct - Performance degraded for Direct and Office | 2018-05-25 09:40 | IMPM-1548 | DPSV-4302 | 2018-05-31 01:49 | 2018-06-12 09:15 | 12.3097 |  |  | Direct/Office
IMPM-1547 | P2 | Direct - Performance degraded for Direct and Office | 2018-05-25 09:40 | IMPM-1548 | DSSV-6633 | 2018-05-31 02:14 | 2018-06-04 03:18 | 4.0444 |  |  | Direct/Office
IMPM-1549 | P2 | Quicktake - Quicktake service degraded | 2018-05-25 15:13 | IMPM-1550 | QT-2609 | 2018-06-03 19:10 | 2018-08-07 01:20 | 64.2569 |  |  | Quicktake
IMPM-1549 | P2 | Quicktake - Quicktake service degraded | 2018-05-25 15:13 | IMPM-1550 | QT-2610 | 2018-06-03 19:13 | 2018-06-08 16:06 | 4.8701 |  |  | Quicktake
IMPM-1549 | P2 | Quicktake - Quicktake service degraded | 2018-05-25 15:13 | IMPM-1550 | QT-2607 | 2018-06-03 18:55 | 2018-06-04 21:13 | 1.0958 |  |  | Quicktake
IMPM-1549 | P2 | Quicktake - Quicktake service degraded | 2018-05-25 15:13 | IMPM-1550 | QT-2608 | 2018-06-03 19:06 | 2018-06-04 21:11 | 1.0868 |  |  | Quicktake
IMPM-1566 | P2 | Quicktake - Performance degraded for multiple products | 2018-05-30 09:20 | IMPM-1568 | QT-2609 | 2018-06-03 19:10 | 2018-08-07 01:20 | 64.2569 |  |  | Quicktake | Same root causes & actions as 1549
IMPM-1566 | P2 | Quicktake - Performance degraded for multiple products | 2018-05-30 09:20 | IMPM-1568 | QT-2610 | 2018-06-03 19:13 | 2018-06-08 16:06 | 4.8701 |  |  | Quicktake | Same root causes & actions as 1549
IMPM-1566 | P2 | Quicktake - Performance degraded for multiple products | 2018-05-30 09:20 | IMPM-1568 | QT-2607 | 2018-06-03 18:55 | 2018-06-04 21:13 | 1.0958 |  |  | Quicktake | Same root causes & actions as 1549
IMPM-1566 | P2 | Quicktake - Performance degraded for multiple products | 2018-05-30 09:20 | IMPM-1568 | QT-2608 | 2018-06-03 19:06 | 2018-06-04 21:11 | 1.0868 |  |  | Quicktake | Same root causes & actions as 1549
IMPM-1573 | P1 | Equity Non Fundamental - Global Equity Price delay has severely degraded multiple exchange related processes | 2018-05-31 20:32 | IMPM-1574 | DCMSD-6486 | 2018-06-07 05:14 | 2018-07-04 04:02 | 26.95 |  |  | Mumbai Support Development
IMPM-1573 | P1 | Equity Non Fundamental - Global Equity Price delay has severely degraded multiple exchange related processes | 2018-05-31 20:32 | IMPM-1574 | RP-5027 | 2018-06-05 08:24 | 2018-07-09 01:46 | 33.7236 |  |  | Research Products
IMPM-1573 | P1 | Equity Non Fundamental - Global Equity Price delay has severely degraded multiple exchange related processes | 2018-05-31 20:32 | IMPM-1574 | DPO-10779 | 2018-06-08 00:37 | 2018-06-08 04:43 | 0.17083 |  |  | Data Operations
IMPM-1575 | P2 | Data API V1- Data API V1 has stale Data | 2018-06-01 14:03 | IMPM-1576 | ENGRTASK-15623 | 2018-06-05 03:20 | 2018-06-28 20:22 | 23.7097 |  |  | Engineering
IMPM-1575 | P2 | Data API V1- Data API V1 has stale Data | 2018-06-01 14:03 | IMPM-1576 | MOCAL-5432 | 2018-06-05 02:20 | 2018-07-08 21:16 | 33.7889 |  |  | Data Products
IMPM-1615 | P1 | Fund Data - APICenter is completely degraded | 2018-06-10 22:34 | IMPM-1616 | CORESVC-4303 | 2018-06-15 02:21 | 2018-08-02 04:52 | 48.1049 |  |  | Core Service
IMPM-1615 | P1 | Fund Data - APICenter is completely degraded | 2018-06-10 22:34 | IMPM-1616 | CORESVC-4318 | 2018-06-22 08:44 | 2018-07-23 01:44 | 30.7083 |  |  | Core Service
IMPM-1615 | P1 | Fund Data - APICenter is completely degraded | 2018-06-10 22:34 | IMPM-1616 | CORESVC-4310 | 2018-06-21 08:13 | 2018-07-30 06:10 | 38.9146 |  |  | Core Service
IMPM-1615 | P1 | Fund Data - APICenter is completely degraded | 2018-06-10 22:34 | IMPM-1616 | CORESVC-4311 | 2018-06-21 08:15 | 2018-06-26 02:29 | 4.7597 |  |  | Core Service
IMPM-1615 | P1 | Fund Data - APICenter is completely degraded | 2018-06-10 22:34 | IMPM-1616 | CORESVC-4312 | 2018-06-21 08:17 | 2018-07-12 01:35 | 20.7208 |  |  | Core Service
IMPM-1632 | P2 | Import Service - MIS Import severly degraded | 2018-06-08 07:30 | IMPM-1634 | DOPA-6177 | 2018-06-13 05:46 | 2018-06-19 04:24 | 5.9431 |  |  | Data Services
IMPM-1632 | P2 | Import Service - MIS Import severly degraded | 2018-06-08 07:30 | IMPM-1634 | CIS-4279 | 2018-06-13 06:35 | 2018-06-14 21:53 | 1.6375 |  |  | Import 3.x
IMPM-1632 | P2 | Import Service - MIS Import severly degraded | 2018-06-08 07:30 | IMPM-1634 | DOPA-6169 | 2018-06-12 23:59 | 2018-07-29 21:12 | 46.884 |  |  | Data Services
IMPM-1632 | P2 | Import Service - MIS Import severly degraded | 2018-06-08 07:30 | IMPM-1634 | CIS-4293 | 2018-06-13 05:46 | 2018-06-19 04:24 | 5.9431 |  |  | Import 3.x
IMPM-1632 | P2 | Import Service - MIS Import severly degraded | 2018-06-08 07:30 | IMPM-1634 | CIS-4300 | 2018-06-20 04:11 | 2018-07-29 20:48 | 39.6924 |  |  | Import 3.x
IMPM-1632 | P2 | Import Service - MIS Import severly degraded | 2018-06-08 07:30 | IMPM-1634 | DDDV-530 | 2018-06-20 04:13 | 2018-08-19 20:34 | 60.6813 |  |  | Client Data Service
IMPM-1632 | P2 | Import Service - MIS Import severly degraded | 2018-06-08 07:30 | IMPM-1634 | DDDV-536 | 2018-06-21 03:42 | 2018-07-12 14:14 | 21.4389 |  |  | Client Data Service
IMPM-1655 | P2 | Data API V2 - Morningstar Analyst Rating in Data API V2 has stale data | 2018-06-21 10:52 | IMPM-1656 | DTC-8202 | 2018-06-21 11:25 | 2018-06-22 11:07 | 0.9875 |  |  | Data Services
IMPM-1690 | P2 | DO - Direct - Performance Degraded for Direct | 2018-07-03 08:01 | IMPM-1695 | IMPM-1695 | 2018-07-03 11:55 | 2018-07-05 16:02 | 2.1715 |  |  | #N/A
IMPM-1702 | P2 | Research Feeds - EXOI Performance Partially Degraded | 2018-07-05 18:42 | IMPM-1703 | MOCAL-5575 | 2018-07-08 22:18 | 2018-07-15 22:11 | 6.9951 |  |  | Data Products
IMPM-1737 | P2 | Data API V2 - Data API V2 has inconsistent versions in prod | 2018-07-13 10:09 | IMPM-1738 | DTPA-3984 | 2018-07-13 10:47 | 2018-09-20 14:38 | 69.1604 |  |  | Data Services
IMPM-1737 | P2 | Data API V2 - Data API V2 has inconsistent versions in prod | 2018-07-13 10:09 | IMPM-1738 | DSO-271 | 2018-07-17 14:00 | 2018-07-19 15:27 | 2.0604 |  |  | Data Services
IMPM-1746 | P2 | DATA API V2 - Portfolio Calculations severely degraded due to big AssetAllocaltion Change | 2018-07-16 23:11 | IMPM-1747 | ENGRTASK-16087 | 2018-07-16 23:21 | 2018-07-17 05:55 | 0.27361 |  |  | Engineering
IMPM-1746 | P2 | DATA API V2 - Portfolio Calculations severely degraded due to big AssetAllocaltion Change | 2018-07-16 23:11 | IMPM-1747 | DOPC-9202 | 2018-07-17 16:10 | 2018-07-24 16:29 | 7.0132 |  |  | Data Services
IMPM-1750 | P1 | Retail Site (US) - Morningstar.com severely degraded | 2018-07-18 06:53 | IMPM-1753 | PHX-14455 | 2018-07-17 16:56 | 2018-07-24 12:14 | 6.8042 |  |  | Phoenix
IMPM-1750 | P1 | Retail Site (US) - Morningstar.com severely degraded | 2018-07-18 06:53 | IMPM-1753 | PHX-14453 | 2018-07-17 16:52 | 2018-07-18 16:17 | 0.97569 |  |  | Phoenix
IMPM-1750 | P1 | Retail Site (US) - Morningstar.com severely degraded | 2018-07-18 06:53 | IMPM-1753 | IISUP-4948 | 2018-07-18 15:57 | 2018-07-20 16:00 | 2.0021 |  |  | Individual Investor Support
IMPM-1775 | P2 | Direct - Delivery Failure Emails being received | 2018-07-21 08:58 | IMPM-1776 | DSSV-7033 | 2018-07-21 11:33 | 2018-07-23 20:39 | 2.3792 |  |  | Direct/Office
IMPM-1775 | P2 | Direct - Delivery Failure Emails being received | 2018-07-21 08:58 | IMPM-1776 | DOV-1902 | 2018-07-26 00:53 | 2018-08-31 03:10 | 36.0951 |  |  | Direct/Office
IMPM-1775 | P2 | Direct - Delivery Failure Emails being received | 2018-07-21 08:58 | IMPM-1776 | DOV-1903 | 2018-07-26 00:58 | 2018-08-06 20:58 | 11.8333 |  |  | Direct/Office
IMPM-1778 | P2 | Direct - Asset Allocation Severely degraded. | 2018-07-22 00:59 | IMPM-1779 | DOV-1908 | 2018-08-08 04:39 | 2018-08-08 04:41 | 0.0013889 |  |  | Direct/Office
IMPM-1780 | P2 | Direct Cloud - Direct Cloud login page severely degraded | 2018-07-22 20:54 | IMPM-1784 | NOTES-3269 | 2018-07-25 09:56 | 2018-07-30 14:43 | 5.1993 |  |  | Notes
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5720 | 2018-07-29 21:38 | 2018-09-07 03:24 | 39.2403 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5719 | 2018-07-29 21:35 | 2018-08-16 01:11 | 17.15 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5716 | 2018-07-26 22:05 | 2018-09-07 03:25 | 42.2222 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5715 | 2018-07-26 22:04 | 2018-09-07 03:25 | 42.2229 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5714 | 2018-07-26 22:04 | 2018-08-16 01:10 | 20.1292 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5713 | 2018-07-26 22:03 | 2018-08-16 01:09 | 20.1292 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5712 | 2018-07-26 22:03 | 2018-08-16 01:09 | 20.1292 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5711 | 2018-07-26 22:02 | 2018-09-07 03:26 | 42.225 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5710 | 2018-07-26 22:01 | 2018-09-07 03:26 | 42.2257 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5709 | 2018-07-26 21:59 | 2018-09-07 03:27 | 42.2278 |  |  | Data Products
IMPM-1791 | P2 | Equity API- AWS service degraded effecting Smart text. | 2018-07-24 04:58 | IMPM-1795 | MOCAL-5708 | 2018-07-26 21:55 | 2018-08-09 02:12 | 13.1785 |  |  | Data Products
IMPM-1793 | P2 | Research Database - Market components degraded, affecting multiple clients. | 2018-07-24 10:54 | IMPM-1800 | DBOPS-11930 | 2018-07-26 21:03 | 2018-08-07 07:13 | 11.4236 |  |  | Database Operation
IMPM-1797 | P2 | Morningstar Storage Service - Slowness for Presentation Studio and Report Portal | 2018-07-24 13:40 | IMPM-1799 | QS-13025 | 2018-07-31 01:34 | 2018-08-03 02:30 | 3.0389 |  |  | Enterprise Component Markets
IMPM-1811 | P2 | Enterprise Component Markets - Issue missing data with Disnat. | 2018-07-30 10:30 | IMPM-1812 | QS-13026 | 2018-07-31 01:46 | 2018-08-16 22:45 | 16.8743 |  |  | Enterprise Component Markets
IMPM-1814 | P2 | Fund XOI Backend - Notification message service from Fund XOI partially degraded | 2018-07-31 22:18 | IMPM-1815 | MOCAL-5757 | 2018-08-07 21:03 | 2018-09-28 01:30 | 51.1854 |  |  | Data Products
IMPM-1814 | P2 | Fund XOI Backend - Notification message service from Fund XOI partially degraded | 2018-07-31 22:18 | IMPM-1815 | DTSMETHODOLOGY-2173 | 2018-08-02 03:35 | 2018-08-02 03:39 | 0.0027778 |  |  | Data Services
IMPM-1816 | P2 | Data API v2 -- missing data for monthly fair value of all stocks from May | 2018-08-01 01:56 | IMPM-1817 | DTC-9134 | 2018-08-24 08:41 | 2018-10-12 17:15 | 49.3569 |  |  | Data Services
IMPM-1816 | P2 | Data API v2 -- missing data for monthly fair value of all stocks from May | 2018-08-01 01:56 | IMPM-1817 | DTC-8977 | 2018-08-23 09:43 | 2018-11-16 13:48 | 85.1701 |  |  | Data Services
IMPM-1816 | P2 | Data API v2 -- missing data for monthly fair value of all stocks from May | 2018-08-01 01:56 | IMPM-1817 | DTC-8624 | 2018-07-26 10:53 | 2018-11-05 18:11 | 102.3042 |  |  | Data Services
IMPM-1830 | P2 | Direct - Service partially degraded. | 2018-08-08 09:38 | IMPM-1831 | DPSV-4741 | 2018-08-09 21:27 | 2018-08-10 02:09 | 0.19583 |  |  | Direct/Office
IMPM-1852 | P2 | Data API V2 - Missing data on Return Index tables | 2018-08-21 12:35 | IMPM-1854 | DTC-9135 | 2018-08-21 16:35 | 2018-09-13 16:33 | 22.9986 |  |  | Data Services
IMPM-1852 | P2 | Data API V2 - Missing data on Return Index tables | 2018-08-21 12:35 | IMPM-1854 | DTC-9166 | 2018-08-21 16:36 | 2018-09-13 16:29 | 22.9951 |  |  | Data Services
IMPM-1852 | P2 | Data API V2 - Missing data on Return Index tables | 2018-08-21 12:35 | IMPM-1854 | DTC-8967 | 2018-08-22 11:40 | 2018-09-14 13:11 | 23.0632 |  |  | Data Services
IMPM-1900 | P1 | Network Storage - Tintri storage severely degraded, affecting multiple products | 2018-09-19 21:08 | IMPM-1903 | ISD-125853 | 2018-09-19 21:08 | 2018-09-20 | 0.11944 |  |  | IT
IMPM-1900 | P1 | Network Storage - Tintri storage severely degraded, affecting multiple products | 2018-09-19 21:08 | IMPM-1903 | ISD-125854 | 2018-09-19 21:08 | 2018-10-20 | 30.1194 |  |  | IT | Target resolve date: 20th October
IMPM-1915 | P2 | Data API V2- Performance degradation for calls to Data API V2 while calling for Morningstar Sustainability Rating | 2018-09-24 13:33 | IMPM-1916 | DTC-9371 | 2018-09-24 10:07 | 2018-09-25 08:55 | 0.95 |  |  | Data Services
IMPM-1915 | P2 | Data API V2- Performance degradation for calls to Data API V2 while calling for Morningstar Sustainability Rating | 2018-09-24 13:33 | IMPM-1916 | DBOPS-12505 | 2018-09-24 14:24 | 2018-09-24 20:20 | 0.24722 |  |  | Database Operation
IMPM-1931 | P2 | Data API V2 - United States Money Market Funds TRI and United States Open-End Funds update ratio is Zero. | 2018-09-28 05:08 | IMPM-1933 | DTC-9247 | 2018-09-07 09:26 | 2019-03-28 15:34 | 184.7854 | 2019-03-31 23:59 | 205.6062 | Data Services
IMPM-1931 | P2 | Data API V2 - United States Money Market Funds TRI and United States Open-End Funds update ratio is Zero. | 2018-09-28 05:08 | IMPM-1933 | DTC-9586 | 2018-10-12 14:58 |  | 248.7854 | 2019-06-03 23:59 | 234.3757 | Data Services |  | Anna Mukhina | Vijaya Laxmi Reddy Narsa
IMPM-1953 | P2 | Research Feeds - GER Production Delayed. | 2018-10-03 21:42 | IMPM-1954 | RP-5453 | 2018-10-05 02:34 | 2019-03-12 05:25 | 155.0951 | 2019-03-07 23:59 | 153.8924 | Research Products
IMPM-1953 | P2 | Research Feeds - GER Production Delayed. | 2018-10-03 21:42 | IMPM-1954 | DPO-12378 | 2018-10-05 05:14 | 2018-11-08 02:04 | 33.8681 |  |  | Data Operations
IMPM-1953 | P2 | Research Feeds - GER Production Delayed. | 2018-10-03 21:42 | IMPM-1954 | DCMSD-6844 | 2018-10-08 07:52 | 2018-10-12 02:19 | 3.7688 |  |  | Mumbai Support Development
IMPM-1961 | P2 | Direct - Presentation Studio partially degraded. | 2018-10-08 18:05 | IMPM-1962 | DPSV-5154 | 2018-10-16 04:32 | 2018-12-06 04:08 | 50.9833 |  |  | Direct/Office
IMPM-1961 | P2 | Direct - Presentation Studio partially degraded. | 2018-10-08 18:05 | IMPM-1962 | DPSV-5116 | 2018-10-09 04:58 | 2018-10-11 05:38 | 2.0278 |  |  | Direct/Office
IMPM-1961 | P2 | Direct - Presentation Studio partially degraded. | 2018-10-08 18:05 | IMPM-1962 | DOV-2029 | 2018-10-16 04:43 | 2018-11-09 02:54 | 23.9243 |  |  | Direct/Office
IMPM-1965 | P2 | Office - PII security issue with Morningstar Office | 2018-10-09 11:35 | IMPM-1970 | DOV-2047 | 2018-10-25 04:53 | 2018-11-26 03:40 | 31.9493 |  |  | Direct/Office
IMPM-1965 | P2 | Office - PII security issue with Morningstar Office | 2018-10-09 11:35 | IMPM-1970 | DOV-2048 | 2018-10-25 04:59 | 2018-11-26 03:41 | 31.9458 |  |  | Direct/Office
IMPM-1965 | P2 | Office - PII security issue with Morningstar Office | 2018-10-09 11:35 | IMPM-1970 | DOV-2049 | 2018-10-25 05:00 | 2018-11-26 03:42 | 31.9458 |  |  | Direct/Office
IMPM-1965 | P2 | Office - PII security issue with Morningstar Office | 2018-10-09 11:35 | IMPM-1970 | DOPA-6981 | 2018-10-18 22:26 | 2018-11-12 02:34 | 24.1722 |  |  | Data Services
IMPM-1965 | P2 | Office - PII security issue with Morningstar Office | 2018-10-09 11:35 | IMPM-1970 | DPSV-5126 | 2018-10-11 00:45 | 2018-10-12 02:05 | 1.0556 |  |  | Direct/Office
IMPM-1965 | P2 | Office - PII security issue with Morningstar Office | 2018-10-09 11:35 | IMPM-1970 | DPSV-5317 | 2018-11-08 11:18 | 2018-11-18 23:28 | 10.5069 |  |  | Direct/Office
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DOPA-7996 | 2018-10-19 14:29 | 2019-04-09 05:10 | 171.6118 | 2019-04-14 23:59 | 177.3958 | Data Services | From DOPC-10438 moved to DOPA -7996
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DOPA-7009 | 2018-10-19 15:48 | 2019-05-09 00:45 | 206.5812 | 2019-05-05 23:59 | 198.341 | Data Services
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DSO-333 | 2018-10-19 09:53 | 2018-11-14 10:24 | 26.0215 |  |  | Data Services | Done in DSO-324
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DOPA-7020 | 2018-10-22 11:22 | 2019-04-04 03:33 | 163.6743 | 2019-03-31 23:59 | 160.5257 | Data Services
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DSBA-84 | 2018-10-22 11:16 | 2018-11-21 00:59 | 29.5715 |  |  | Data Services
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DOPA-7087 | 2018-10-22 11:25 | 2019-04-07 20:51 | 167.3931 | 2019-03-31 23:59 | 160.5236 | Data Services
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DSO-337 | 2018-10-22 11:30 |  | 235.5812 | 2019-06-03 23:59 | 224.5201 | Data Services |  | Antonio Morales | Vijaya Laxmi Reddy Narsa
IMPM-1972 | P2 | DataAPI V2- DataAPI V2 service degraded. | 2018-10-11 10:02 | IMPM-1973 | DSBA-85 | 2018-10-22 11:31 | 2019-05-13 21:39 | 220.5812 | 2019-05-19 23:59 | 209.5194 | Data Services |  | Donglin Liu | Vijaya Laxmi Reddy Narsa
IMPM-1980 | P2 | ECINT - Custom Tools partially Degraded | 2018-10-15 17:07 | IMPM-1981 | MISUPGRADE-3981 | 2018-10-16 14:30 | 2018-10-16 16:35 | 0.086806 |  |  | Managed Portfolios Platform Upgrade
IMPM-2001 | P2 | Data Service - Morningstar Storage Service is partially degraded | 2018-10-24 12:41 | IMPM-2004 | DOPA-7081 | 2018-10-31 03:42 | 2018-11-19 03:00 | 18.9708 |  |  | Data Services
IMPM-2001 | P2 | Data Service - Morningstar Storage Service is partially degraded | 2018-10-24 12:41 | IMPM-2004 | DOPA-7059 | 2018-10-29 00:54 | 2018-11-04 19:51 | 6.7896 |  |  | Data Services
IMPM-2061 | P2 | Research Database - GFR severely degraded | 2018-11-15 19:12 | IMPM-2064 | DPO-13035 | 2018-11-20 00:03 | 2018-12-18 02:59 | 28.1222 |  |  | Data Operations
IMPM-2061 | P2 | Research Database - GFR severely degraded | 2018-11-15 19:12 | IMPM-2064 | DPO-13038 | 2018-11-20 00:09 | 2018-12-13 01:37 | 23.0611 |  |  | Data Operations
IMPM-2061 | P2 | Research Database - GFR severely degraded | 2018-11-15 19:12 | IMPM-2064 | PDFR-4114 | 2018-11-14 13:37 | 2018-12-05 12:18 | 20.9451 |  |  | PDF Reports
IMPM-2080 | P2 | Direct- MorningStar Direct Presentation Studio Partially Degraded | 2018-11-28 15:17 | IMPM-2081 | DPSV-5453 | 2018-11-29 01:10 | 2018-12-07 03:08 | 8.0819 |  |  | Direct/Office
IMPM-2080 | P2 | Direct- MorningStar Direct Presentation Studio Partially Degraded | 2018-11-28 15:17 | IMPM-2081 | DPSV-5475 | 2018-11-29 23:17 | 2018-12-07 03:09 | 7.1611 |  |  | Direct/Office
IMPM-2080 | P2 | Direct- MorningStar Direct Presentation Studio Partially Degraded | 2018-11-28 15:17 | IMPM-2081 | DPSV-5534 | 2018-12-11 | 2018-12-11 00:31 | 0.021528 |  |  | Direct/Office
IMPM-2107 | P2 | Direct - Excel API Add-in service degraded | 2018-12-10 10:18 | IMPM-2108 | DOV-2136 | 2018-12-17 02:09 | 2019-01-16 21:39 | 30.8125 | 2019-01-16 | 29.9104 | Direct/Office
IMPM-2107 | P2 | Direct - Excel API Add-in service degraded | 2018-12-10 10:18 | IMPM-2108 | DOV-2140 | 2018-12-17 02:56 | 2019-02-12 01:06 | 56.9236 | 2019-02-01 23:59 | 46.8771 | Direct/Office
IMPM-2107 | P2 | Direct - Excel API Add-in service degraded | 2018-12-10 10:18 | IMPM-2108 | DOV-2137 | 2018-12-17 02:11 | 2018-12-24 02:26 | 7.0104 |  |  | Direct/Office
IMPM-2107 | P2 | Direct - Excel API Add-in service degraded | 2018-12-10 10:18 | IMPM-2108 | DOV-2138 | 2018-12-17 02:46 | 2018-12-24 23:58 | 7.8833 |  |  | Direct/Office
IMPM-2107 | P2 | Direct - Excel API Add-in service degraded | 2018-12-10 10:18 | IMPM-2108 | DOV-2139 | 2018-12-17 02:54 | 2018-12-25 00:54 | 7.9167 |  |  | Direct/Office
IMPM-2169 | P2 | Equity API - Equity API Webservice is Partially Degraded | 2019-01-03 11:01 | IMPM-2170 | MOCAL-6425 | 2019-01-04 01:26 | 2019-01-10 02:20 |  |  |  | Data Products
IMPM-2184 | P2 | AWS - Hit with SQL Injection impacting ReleaseLive DB | 2019-01-10 10:29 | IMPM-2185 | AWSE-30588 | 2019-01-31 23:50 | 2019-04-09 22:25 | 67.941 | 2019-04-09 23:59 | 68.0062 | Advisor Workstation
IMPM-2195 | P2 | Data Messaging - Kafka service partially degraded | 2019-01-14 03:27 | IMPM-2197 | KAFKA-1657 | 2018-12-04 09:32 | 2019-03-20 10:52 | 76.8556 | 2019-03-31 23:59 | 117.6021 | Kafka
IMPM-2195 | P2 | Data Messaging - Kafka service partially degraded | 2019-01-14 03:27 | IMPM-2197 | KAFKA-1924 | 2019-02-27 13:56 | 2019-03-06 13:13 | 52.8556 | 2019-03-07 23:59 | 8.4187 | Kafka
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | 2019-01-16 20:54 | IMPM-2214 | DTPA-4610 | 2019-01-23 11:35 |  | 138.1285 | 2019-06-03 23:59 | 131.5167 | Data Services |  | Donglin Liu | Antonio Morales
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | 2019-01-16 20:54 | IMPM-2214 | DOPC-11706 | 2019-01-23 11:46 | 2019-03-04 15:24 | 50.1285 | 2019-03-07 23:59 | 43.509 | Data Services
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | 2019-01-16 20:54 | IMPM-2214 | DOPC-11542 | 2019-01-10 11:31 | 2019-01-29 10:27 | 18.9556 | 2019-01-27 | 16.5201 | Data Services
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | 2019-01-16 20:54 | IMPM-2214 | DSO-454 | 2019-01-23 11:41 |  | 138.1285 | 2019-06-03 23:59 | 131.5125 | Data Services |  | Unassigned | Antonio Morales
IMPM-2213 | P2 | Data API V2 - Portfolio ownership API performance degraded | 2019-01-16 20:54 | IMPM-2214 | DSO-455 | 2019-01-23 11:53 |  | 138.1285 | 2019-06-03 23:59 | 131.5042 | Data Services |  | Unassigned | Antonio Morales
IMPM-2215 | P2 | Data API V2 - Portfolio Account holding imports degraded | 2019-01-16 22:33 | IMPM-2216 | DSO-451 | 2019-01-22 15:07 |  | 138.0597 | 2019-06-03 23:59 | 132.3694 | Data Services |  | Unassigned | Antonio Morales
IMPM-2215 | P2 | Data API V2 - Portfolio Account holding imports degraded | 2019-01-16 22:33 | IMPM-2216 | DOPC-11684 | 2019-01-22 15:13 | 2019-05-31 15:07 | 123.0597 | 2019-05-19 23:59 | 117.3653 | Data Services |  | Ishita Shah | Antonio Morales
IMPM-2215 | P2 | Data API V2 - Portfolio Account holding imports degraded | 2019-01-16 22:33 | IMPM-2216 | DOPC-11605 | 2019-01-15 14:45 | 2019-01-23 10:57 |  |  |  | Data Services
IMPM-2234 | P2 | Fund Portfolio - Portfolio Partially Degraded | 2019-01-30 16:01 | IMPM-2235 | DTSMETHODOLOGY-3066 | 2019-02-25 21:03 | 2019-04-18 04:42 | 51.3187 | 2019-04-14 23:59 | 48.1222 | Data Services
IMPM-2234 | P2 | Fund Portfolio - Portfolio Partially Degraded | 2019-01-30 16:01 | IMPM-2235 | MRDPM-18600 | 2019-03-20 01:58 | 2019-04-03 21:56 | 14.8319 | 2019-04-02 23:59 | 13.9174 | Data Collection
IMPM-2236 | P2 | AWS - Service Partially degraded for clients Ameriprise and Wells Fargo | 2019-01-31 03:49 | IMPM-2237 | AWSE-30585 | 2019-01-31 15:06 | 2019-04-30 15:01 | 88.9965 | 2019-04-14 23:59 | 73.3701 | Advisor Workstation
IMPM-2236 | P2 | AWS - Service Partially degraded for clients Ameriprise and Wells Fargo | 2019-01-31 03:49 | IMPM-2237 | AWSE-30372 | 2019-01-17 16:59 | 2019-02-06 14:42 |  |  |  | Advisor Workstation
IMPM-2266 | P2 | Equity Data Feeds - Multiple clients reported earning reports data missing in delta file since 1/31 | 2019-02-12 11:56 | IMPM-2267 | MOCAL-6567 | 2019-02-09 19:40 | 2019-02-12 22:02 |  |  |  | Data Products
IMPM-2266 | P2 | Equity Data Feeds - Multiple clients reported earning reports data missing in delta file since 1/31 | 2019-02-12 11:56 | IMPM-2267 | MOCAL-6582 | 2019-02-13 00:35 | 2019-03-20 02:54 |  | 2019-03-17 23:59 | 32.975 | Data Products
IMPM-2272 | P2 | Office Cloud - Client Web Portal is completely Degraded | 2019-02-15 09:49 | IMPM-2273 | OC-3826 | 2019-03-06 01:54 | 2019-03-25 00:07 |  | 2019-03-17 23:59 | 11.9201 | Office Cloud
IMPM-2272 | P2 | Office Cloud - Client Web Portal is completely Degraded | 2019-02-15 09:49 | IMPM-2273 | OC-3876 | 2019-03-12 01:58 | 2019-03-25 22:53 |  | 2019-03-17 23:59 | 5.9174 | Office Cloud
IMPM-2272 | P2 | Office Cloud - Client Web Portal is completely Degraded | 2019-02-15 09:49 | IMPM-2273 | OC-3877 | 2019-03-12 02:46 | 2019-04-25 22:43 | 44.8313 | 2019-04-26 23:59 | 45.884 | Office Cloud
IMPM-2272 | P2 | Office Cloud - Client Web Portal is completely Degraded | 2019-02-15 09:49 | IMPM-2273 | OC-3875 | 2019-03-12 01:56 | 2019-03-12 04:38 |  |  |  | Office Cloud
IMPM-2277 | P2 | Research Feeds - USA Production Delayed. | 2019-02-19 18:09 | IMPM-2278 | DCMSD-7150 | 2019-02-22 04:31 |  | 104.2431 | 2019-06-03 23:59 | 101.8111 | Mumbai Support Development |  | Sameera Ahmed | Mangesh Chavan
IMPM-2286 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | 2019-02-22 10:31 | IMPM-2287 | ISD-152763 | 2019-02-22 01:59 | 2019-02-22 15:11 |  |  |  | IT
IMPM-2286 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | 2019-02-22 10:31 | IMPM-2287 | DTC-11134 | 2019-02-25 15:58 | 2019-03-13 15:21 | 13.5611 | 2019-03-07 23:59 | 10.334 | Data Services
IMPM-2286 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | 2019-02-22 10:31 | IMPM-2287 | DTS-2379 | 2019-02-25 11:56 |  | 101.5611 | 2019-06-03 23:59 | 98.5021 | Data Services |  | Unassigned | Vijaya Laxmi Reddy Narsa
IMPM-2286 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | 2019-02-22 10:31 | IMPM-2287 | DOPC-12266 | 2019-02-25 16:02 | 2019-03-14 12:04 | 13.5611 | 2019-03-07 23:59 | 10.3312 | Data Services
IMPM-2286 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | 2019-02-22 10:31 | IMPM-2287 | DE-286 | 2019-02-25 16:08 | 2019-05-01 14:47 | 64.9437 | 2019-04-30 23:59 | 64.3271 | Data Services |  | Eileen Bingle | Vijaya Laxmi Reddy Narsa
IMPM-2286 | P2 | Data API V2 - Merrill Lynch account files not successfully processed | 2019-02-22 10:31 | IMPM-2287 | DSO-490 | 2019-02-22 09:58 | 2019-02-26 10:52 |  |  |  | Data Services
IMPM-2295 | P2 | Import Service - Merrill Lynch account files not successfully processed | 2019-02-26 15:43 | IMPM-2298 | PBCIMPORT-5032 | 2019-01-16 20:08 | 2019-02-26 10:52 | 9.3444 | 2019-03-07 23:59 | 50.1604 | Import
IMPM-2295 | P2 | Import Service - Merrill Lynch account files not successfully processed | 2019-02-26 15:43 | IMPM-2298 | PBCIMPORT-5161 | 2019-02-27 22:21 | 2019-04-15 20:23 | 46.9181 | 2019-04-26 23:59 | 58.0681 | Import
IMPM-2322 | P2 | Direct Cloud - Office cloud's service partially degraded by a scheduled patch release | 2019-03-06 22:39 | IMPM-2323 | OC-3831 | 2019-03-06 20:11 | 2019-03-07 04:29 |  |  |  | Office Cloud
IMPM-2322 | P2 | Direct Cloud - Office cloud's service partially degraded by a scheduled patch release | 2019-03-06 22:39 | IMPM-2323 | OC-3840 | 2019-03-07 04:07 | 2019-03-15 03:16 |  |  |  | Office Cloud
IMPM-2330 | P2 | Data API V2 - Data API V2 Performance Degraded | 2019-03-15 04:42 | IMPM-2331 | NOTES-3754 | 2019-02-18 19:27 | 2019-03-21 05:09 |  |  |  | Notes
IMPM-2330 | P2 | Data API V2 - Data API V2 Performance Degraded | 2019-03-15 04:42 | IMPM-2331 | DOPC-8457 | 2018-05-07 06:54 | 2018-07-30 20:50 |  |  |  | Data Services
IMPM-2342 | P2 | Retail Sites (AU) - My Portfolio tab in morningstar.com.au is partially degraded | 2019-03-24 18:52 | IMPM-2343 | IISUP-5591 | 2019-03-26 03:13 | 2019-04-24 03:04 | 42.2132 | 2019-05-05 23:59 | 40.8653 | Individual Investor Support | Share the same action items with IMPM-2344
IMPM-2342 | P2 | Retail Sites (AU) - My Portfolio tab in morningstar.com.au is partially degraded | 2019-03-24 18:52 | IMPM-2343 | IISUP-5592 | 2019-03-26 03:15 |  | 71.2132 | 2019-06-03 23:59 | 69.8639 | Individual Investor Support |  | Unassigned | Navy Huang
IMPM-2342 | P2 | Retail Sites (AU) - My Portfolio tab in morningstar.com.au is partially degraded | 2019-03-24 18:52 | IMPM-2343 | IISUP-5593 | 2019-03-26 03:55 | 2019-03-26 04:17 |  |  |  | Individual Investor Support
IMPM-2358 | P2 | Office Cloud - Client Web Portal login degraded | 2019-04-01 13:17 | IMPM-2359 | OC-4000 | 2019-04-02 04:30 | 2019-04-02 09:43 | 0.21736 | 2019-04-26 23:59 | 24.8118 | Office Cloud
IMPM-2358 | P2 | Office Cloud - Client Web Portal login degraded | 2019-04-01 13:17 | IMPM-2359 | DOPA-8086 | 2019-04-02 20:41 | 2019-05-29 02:57 | 48.4458 | 2019-05-19 23:59 | 47.1375 | Data Services
IMPM-2358 | P2 | Office Cloud - Client Web Portal login degraded | 2019-04-01 13:17 | IMPM-2359 | OC-4063 | 2019-04-12 01:08 | 2019-05-08 03:11 | 34.4458 | 2019-05-05 23:59 | 23.9521 | Office Cloud
IMPM-2358 | P2 | Office Cloud - Client Web Portal login degraded | 2019-04-01 13:17 | IMPM-2359 | OC-4065 | 2019-04-12 01:19 | 2019-04-22 21:33 | 25.4458 | 2019-04-26 23:59 | 14.9444 | Office Cloud
IMPM-2358 | P2 | Office Cloud - Client Web Portal login degraded | 2019-04-01 13:17 | IMPM-2359 | OC-4064 | 2019-04-12 01:08 | 2019-05-08 03:11 | 34.4458 | 2019-05-05 23:59 | 23.9521 | Office Cloud
IMPM-2384 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | 2019-04-15 11:25 | IMPM-2385 | QT-2801 | 2019-04-17 05:23 |  | 49.5236 | 2019-06-03 23:59 | 47.775 | Quicktake
IMPM-2384 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | 2019-04-15 11:25 | IMPM-2385 | QT-2807 | 2019-04-19 04:39 | 2019-04-19 04:40 | 11.5236 | 2019-04-26 23:59 | 7.8056 | Quicktake
IMPM-2384 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | 2019-04-15 11:25 | IMPM-2385 | SAL-4116 | 2019-04-19 04:35 |  | 49.5236 | 2019-06-03 23:59 | 45.8083 | SAL
IMPM-2384 | P2 | Quicktake - Quicktake chart data is degraded for multiple EC clients | 2019-04-15 11:25 | IMPM-2385 | QT-2806 | 2019-04-22 03:54 |  | 49.5236 | 2019-06-03 23:59 | 42.8368 | Quicktake
IMPM-2386 | P2 | Market Data Binary Feed Delivery - Lag in streaming options for quotes for DISNAT | 2019-04-16 22:36 | IMPM-2387 | RT-22869 | 2019-04-17 23:38 | 2019-05-03 02:26 | 15.1167 | 2019-04-30 23:59 | 13.0146 | Real Time
IMPM-2386 | P2 | Market Data Binary Feed Delivery - Lag in streaming options for quotes for DISNAT | 2019-04-16 22:36 | IMPM-2387 | RT-22870 | 2019-04-18 00:09 |  | 48.0576 | 2019-06-03 23:59 | 46.9931 | Real Time
IMPM-2395 | P2 | Research Database - Intermittent RDB Outage in the weekend | 2019-04-22 10:09 | IMPM-2396 | DBOPS-14820 | 2019-04-23 05:41 |  | 42.5764 | 2019-06-03 23:59 | 41.7625 | Database Operation
IMPM-2395 | P2 | Research Database - Intermittent RDB Outage in the weekend | 2019-04-22 10:09 | IMPM-2396 | DSO-588 | 2019-04-24 18:24 |  | 42.5764 | 2019-06-03 23:59 | 40.2326 | Data Services
IMPM-2395 | P2 | Research Database - Intermittent RDB Outage in the weekend | 2019-04-22 10:09 | IMPM-2396 | DTC-12096 | 2019-04-29 15:59 |  | 42.5764 | 2019-06-03 23:59 | 35.3333 | Data Services
IMPM-2399 | P2 | Data API V2 - 1 Year Return" is duplicated incorrectly with the "YTD % | 2019-04-23 12:56 | IMPM-2401 | DOPC-12617 | 2019-04-15 14:22 | 2019-05-17 14:55 | 26.4604 | 2019-05-19 23:59 | 34.4007 | Data Services
IMPM-2399 | P2 | Data API V2 - 1 Year Return" is duplicated incorrectly with the "YTD % | 2019-04-23 12:56 | IMPM-2401 | DTPA-4974 | 2019-04-24 19:13 | 2019-05-14 09:46 | 26.4604 | 2019-05-19 23:59 | 25.1986 | Data Services
IMPM-2399 | P2 | Data API V2 - 1 Year Return" is duplicated incorrectly with the "YTD % | 2019-04-23 12:56 | IMPM-2401 | ENGRTASK-19008 | 2019-04-08 14:19 | 2019-04-19 03:10 | 3.4604 | 2019-04-26 23:59 | 18.4028 | Engineering
IMPM-2406 | P2 | Equity API - Equity API Webservices Partially Degraded | 2019-04-30 12:08 | IMPM-2407 | MOCAL-6949 | 2019-05-02 01:00 | 2019-05-28 01:44 | 19.4937 | 2019-05-19 23:59 | 17.9576 | Data Products
IMPM-2416 | P2 | Retail Sites AU - MCA - Portfolio manager is down | 2019-05-09 20:07 | IMPM-2417 | IISUP-5709 | 2019-05-12 22:23 | 2019-05-29 03:55 | 10.1611 | 2019-05-19 23:59 | 7.0667 | Individual Investor Support
IMPM-2416 | P2 | Retail Sites AU - MCA - Portfolio manager is down | 2019-05-09 20:07 | IMPM-2417 | ISD-168140 | 2019-05-13 22:13 |  | 25.1611 | 2019-06-03 23:59 | 21.0736 | IT
IMPM-2418 | P2 | Office - UIS import service partially degraded | 2019-05-13 05:48 | IMPM-2419 | CIS-5151 | 2019-05-27 03:59 |  | 21.7576 | 2019-06-03 23:59 | 7.8333 | Import 3.x
IMPM-2418 | P2 | Office - UIS import service partially degraded | 2019-05-13 05:48 | IMPM-2419 | CIS-5152 | 2019-05-27 04:13 |  | 21.7576 | 2019-06-03 23:59 | 7.8236 | Import 3.x
IMPM-2418 | P2 | Office - UIS import service partially degraded | 2019-05-13 05:48 | IMPM-2419 | DOPA-8549 | 2019-05-31 02:51 |  | 21.7576 | 2019-06-03 23:59 | 3.8806 | Data Services
IMPM-2418 | P2 | Office - UIS import service partially degraded | 2019-05-13 05:48 | IMPM-2419 | DOPA-8550 | 2019-05-31 02:53 |  | 21.7576 | 2019-06-03 23:59 | 3.8792 | Data Services
IMPM-2418 | P2 | Office - UIS import service partially degraded | 2019-05-13 05:48 | IMPM-2419 | DOPA-8553 | 2019-05-31 03:13 |  | 21.7576 | 2019-06-03 23:59 | 3.8653 | Data Services
IMPM-2420 | P2 | Office - Import process partially degraded for UK clients | 2019-05-13 11:24 | IMPM-2421 | CIS-5151 | 2019-05-27 03:59 |  | 21.5243 | 2019-06-03 23:59 | 7.8333 | Import 3.x
IMPM-2430 | P2 | Equity Non-Fundamental - Delay in Equity Rating USA file | 2019-05-17 17:56 | IMPM-2431 | DCMSD-7414 | 2019-05-31 08:15 |  | 17.2521 | 2019-06-03 23:59 | 3.6556 | Mumbai Support Development

## JIRA Project Mapping
Jira Key | Team Name | Sub-team
AWSE | Advisor Workstation
APPOPS | IT | ITOps
IOT | IT | IT Operation - Tools
ISD | IT | IT Service Desk
CIS | Import 3.x
CORESVC | Core Service
DBOPS | Database Operation
DCF | Direct Cloud | Direct Cloud Framework
DCMSD | Mumbai Support Development
DDDV | Client Data Service
DOV | Direct/Office | Direct/Office - Operation V2
DPSV | Direct/Office | Presentation Studio
DSSV | Direct/Office | Direct/Office - Shared Service V2
DE | Data Services | Data Entitlement
DSO | Data Services | Data Services - Operations
DSBA | Data Services | Data Services - Business Analysis
DTC | Data Services | Data Tech - Content
DTS | Data Services | Data Tech - Support
DTPA | Data Services | Data Tech - Platform API
DOPA | Data Services
DOPC | Data Services | Direct/Office - Portfolio API
DTSMETHODOLOGY | Data Services | Methodology (Fund & Bond)
DPO | Data Operations
ENGRTASK | Engineering
IISUP | Individual Investor Support
INSTSRE | Institutional Products SRE
INTL | International Tools & Data Feed Products
MOCAL | Data Products
MRDPM | Data Collection
NEWS | News
OC | Office Cloud
QS | Enterprise Component Markets
QT | Quicktake
RP | Research Products
RT | Real Time
PHX | Phoenix
Notes | Notes
MISUPGRADE | Managed Portfolios Platform Upgrade
PDFR | PDF Reports
PBCIMPORT | Import | PBC Portfolio Import
KAFKA | Kafka | Kafka Messaging
SAL | SAL